## Research Impl
| 2020 | 2021
| Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Analysis plan | bar: 2020 Dec to 2021 Jan
Setting up environment: storage | bar: 2021 Jan to 2021 Feb
Data transfer | bar: 2021 Mar
QC statistics | bar: 2021 Mar to 2021 Apr
Gene-based annotation | bar: 2021 Apr to 2021 May
Description of data | bar: 2021 May to 2021 Jun
Prioritise top signals | bar: 2021 Jun to 2021 Jul; 2021 Sep
Followup search for causal + functional variants | bar: 2021 Sep to 2021 Oct
Interpretation and analysis of results | bar: 2021 Oct to 2021 Dec

## Setup
Month | January |  |  | February |  |  | February |  |  | February |  |  | February
Week | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5
Dates | Fri-29 | Sat-30 | Sun-31 | Fri-05 | Sat-06 | Sun-07 | Fri-12 | Sat-13 | Sun-14 | Fri-19 | Sat-20 | Sun-21 | Fri-26 | Sat-27 | Sun-28
Times | 7.20-8.30am | 11.00-12.00am | 3.00-4.00pm | 7.20-8.30am | 11.00-12.00am | 3.00-4.00pm | 7.20-8.30am | 11.00-12.00am | 3.00-4.00pm | 7.20-8.30am | 11.00-12.00am | 3.00-4.00pm | 7.20-8.30am | 11.00-12.00am | 3.00-4.00pm
Metalearning | bar: 1 Fri-29
Mount EFS from EC2 | bar: 1 Sat-30
GitHub repo cloud + local | bar: 1 Sun-31
Load ANNOVAR dbs + follow startup guide | bar: 2 Fri-05
Test ANNOVAR with an exome: prep input files | bar: 2 Sat-06
Test ANNOVAR with an exome: follow gene-based annotation | bar: 2 Sun-07
Test ANNOVAR with an exome: filter based annotation | bar: 2 Sun-07
Assign annotations found in ClinVar | bar: 3 Fri-12
Assign annotations found in gnomAD | bar: 3 Sat-13
Assess VEP differences with ANNOVAR | bar: 3 Sun-14
Assess whether it is worth installing VEP | bar: 3 Sun-14
Test ANNOVAR with infection susceptibility panel | bar: 4 Fri-19
Test annovar with Immunological response | bar: 4 Sat-20
Test ANNOVAR with direct determinants of disease severity | bar: 4 Sun-21
Install BWA +GATK | bar: 5 Fri-26
Run example | bar: 5 Sat-27 to 5 Sun-28